## Product Backlog
Sharks EventBrite Platform — Product Backlog
Story ID | User Story | Priority | Pts | Sprint | Status | Owner | Component | Acceptance Criteria | Notes
US-01 | As a user I can register with name, email, password and role | High | 5 | 3 | Done | Ankush | Auth Service | User created in Supabase with role in user_metadata; JWT returned | GoTrue /signup
US-02 | As a user I can log in and receive a JWT token | High | 5 | 3 | Done | Ankush | Auth Service | 200 response with access_token from AWS backend | AuthController
US-03 | As a user I am redirected based on my role after login | High | 3 | 3 | Done | Maurin | Frontend | Admin→dashboard, Organizer→org view, Attendee→home | Role from JWT
US-04 | As an attendee I can browse events with search and filters | High | 5 | 3 | Done | Maurin | Frontend | Filterable by category, date, location, keyword | React UI
US-05 | As an attendee I can view event detail with map and schedule | High | 3 | 3 | Done | Maurin | Frontend | Map shown, schedule and organizer info visible | Google Maps
US-06 | As an attendee I can register and purchase tickets | High | 5 | 2 | Done | Maurin | Frontend / Payment | Ticket created with code; mock payment flow | Mock Stripe UI
US-07 | As an attendee I can add an event to Google Calendar | Medium | 3 | 2 | Done | Maurin | Frontend | Calendar link opens with event details pre-filled | URL integration
US-08 | As an organizer I can create events with all details | High | 8 | 4 | Done | Aniket | User & Org Service | Event saved with title, date, time, location, capacity, price | Pending approval
US-09 | As an organizer I can view my event attendee list | High | 5 | 5 | Done | Aniket | User & Org Service | RSVP list shows name, email, ticket status | Org ownership check
US-10 | As an organizer I can edit or cancel my events | Medium | 5 | 4 | Done | Aniket | User & Org Service | Changes reflected immediately; attendees notified | RabbitMQ event
US-11 | As an admin I can approve or reject organizer events | High | 5 | 5 | Done | Maurin | Frontend / Auth | Event status changes; visible to organizer | Admin role required
US-12 | As an admin I can view all users and manage roles | High | 3 | 5 | Done | Maurin | Frontend | User list with role badges in admin dashboard
US-13 | As an admin I can view platform-wide statistics | Medium | 3 | 5 | Done | Maurin | Frontend | Shows total users, events, tickets, revenue | Mock stats
US-14 | RabbitMQ pub-sub messaging pipeline across all services | High | 8 | 2 | Done | Ankush | Infrastructure | Auth publishes user.provisioned; user service consumes | 3 exchanges, topic routing
US-15 | Docker Compose and RabbitMQ container with pre-loaded definitions | High | 5 | 2 | Done | Ankush | Infrastructure | docker-compose up starts broker with correct exchanges/queues | definitions.json
US-16 | Supabase database migrations for user roles and RLS | High | 5 | 1 | Done | Ankush | Auth Service / DB | user_roles table with RLS; JWT custom claims | 4 migration files
US-17 | Deploy auth service to AWS Elastic Beanstalk with ALB | High | 8 | 3 | Done | Maurin | Cloud / DevOps | ALB with min 2 EC2 instances routing through Spring Cloud Gateway | sharks-auth-prod
US-18 | Spring Cloud Gateway service as routing layer for backend microservices | High | 5 | 6 | Done | Maurin | Cloud / DevOps | HTTPS endpoint routing to ELB; no mixed-content errors | Spring Boot routing
US-19 | Connect custom domain sharks-eventbrite.live | Medium | 3 | 6 | Done | Maurin | Cloud / DevOps | DNS configured; SSL issued; site loads on custom domain
US-20 | Email/notification service for ticket confirmations | Medium | 5 | 6 | In Progress | Aniket | Infrastructure | Confirmation sent via RabbitMQ consumer after purchase | Stub implemented
US-21 | Secure API with input validation and error handling | High | 5 | 3 | Done | Ankush | Auth Service | 400 errors for invalid inputs; AuthExceptionHandler | Global exception handler
US-22 | Responsive UI for web and mobile devices | Medium | 3 | 3 | Done | Maurin | Frontend | UI renders correctly on mobile and desktop | React responsive

## Sprint 1
Sprint 1 Backlog — Feb 9 – Feb 22, 2026
Story ID | Task | Assignee | Est. Pts | Actual Pts | Status | Start | End
US-15 | Set up dev environment (Java 17, Gradle, IDE) and initialize Spring Boot auth service | Ankush | 3 | 3 | Done | Feb 9 | Feb 11
US-16 | Write Supabase DB migrations: init_app_role_and_user_roles, user_roles_rls (RLS policies) | Ankush | 5 | 5 | Done | Feb 11 | Feb 15
US-01 | Design auth API endpoints contract (login, register, JWT) and implement SupabaseAuthClient | Ankush | 3 | 3 | Done | Feb 15 | Feb 18
US-02 | Implement AuthController POST /api/v1/auth/login + AppRole enum, UserRole, SupabaseProperties | Ankush | 3 | 3 | Done | Feb 18 | Feb 22
US-15 | Set up Docker dev environment and initialize User & Organizations Spring Boot service | Aniket | 3 | 3 | Done | Feb 9 | Feb 12
US-14 | Design Queue schema: RabbitMQ exchange/queue topology and document MESSAGING.md | Aniket | 5 | 5 | Done | Feb 12 | Feb 16
US-08 | Define data schema: UserProfile and Organization entities + UserDto, OrganizationDto, CreateOrganizationRequest DTOs | Aniket | 3 | 3 | Done | Feb 16 | Feb 19
US-08 | Implement UserProfileRepository and OrganizationRepository (Spring Data JPA) | Aniket | 2 | 2 | Done | Feb 19 | Feb 22
US-22 | Set up frontend dev environment (Vite, React, TypeScript, Tailwind, shadcn/ui) and team GitHub repo | Maurin | 2 | 2 | Done | Feb 9 | Feb 11
US-03 | Initialize React/TypeScript frontend with React Router and role-based routing scaffolding | Maurin | 2 | 2 | Done | Feb 11 | Feb 13
US-04 | Build Login and Signup UI with form validation and create api.ts contract (request/response shapes) | Maurin | 3 | 3 | Done | Feb 13 | Feb 17
US-22 | Design initial Component diagram (system architecture across frontend, services, RabbitMQ, Supabase) | Maurin | 3 | 3 | Done | Feb 17 | Feb 20
US-08 | Design initial ER diagram (User, Event, Ticket, Organization data model) | Maurin | 3 | 3 | Done | Feb 20 | Feb 22
TOTAL | 13/13 tasks completed

## Sprint 2
Sprint 2 Backlog — Feb 23 – Mar 8, 2026
Story ID | Task | Assignee | Est. Pts | Actual Pts | Status | Start | End
US-02 | Implement JWT validation using Supabase JWT issuer (oauth2ResourceServer) | Ankush | 3 | 3 | Done | Feb 23 | Feb 25
US-21 | Configure SecurityConfig CORS, InternalApiKeyAuthFilter, RequestIdFilter | Ankush | 3 | 3 | Done | Feb 25 | Feb 27
US-21 | Implement SupabaseAdminClient and UserProvisioningService for role assignment on signup | Ankush | 3 | 3 | Done | Feb 27 | Mar 1
US-16 | Write Supabase DB migrations: seed_user_roles, jwt_custom_claims, auto_role_on_signup | Ankush | 4 | 4 | Done | Mar 1 | Mar 4
US-01 | Implement /api/v1/auth/register endpoint + UserEventPublisher publishing user.provisioned events | Ankush | 3 | 3 | Done | Mar 4 | Mar 6
US-21 | Add RabbitMqConfig with Jackson2JsonMessageConverter + write unit tests (AuthControllerTest, SupabaseAuthClientTest, UserProvisioningServiceTest) | Ankush | 3 | 3 | Done | Mar 6 | Mar 8
US-08 | Implement REST endpoints for user profile (GET/PUT/PATCH /api/v1/users/me, password change) | Aniket | 3 | 3 | Done | Feb 23 | Feb 26
US-08 | Implement REST endpoints for organizations (GET/POST /api/v1/organizations, GET by id) | Aniket | 3 | 3 | Done | Feb 26 | Mar 1
US-15 | Set up RabbitMQ Docker image with pre-loaded exchange/queue definitions via definitions.json | Aniket | 3 | 3 | Done | Mar 1 | Mar 4
US-15 | Configure docker-compose.yml for local dev orchestrating Postgres + RabbitMQ + services | Aniket | 2 | 2 | Done | Mar 4 | Mar 6
US-14 | Implement UserCreatedListener + OrganizationEventPublisher + RabbitMqConfig with Jackson converter | Aniket | 4 | 4 | Done | Mar 6 | Mar 8
US-04 | Build event discovery page with search bar, category filters, date and location filters | Maurin | 3 | 3 | Done | Feb 23 | Feb 26
US-05 | Build event detail page (description, schedule, organizer info, Google Maps embed) + Google Calendar integration link | Maurin | 3 | 3 | Done | Feb 26 | Mar 1
US-06 | Build My Tickets page with ticket codes, quantities, and status badges | Maurin | 2 | 2 | Done | Mar 1 | Mar 4
US-22 | Finalize UML Component diagram (service boundaries, integrations, exchanges) | Maurin | 3 | 3 | Done | Mar 4 | Mar 8
TOTAL | 15/15 tasks completed

## Sprint 3
Sprint 3 Backlog — Mar 9 – Mar 22, 2026 (light sprint)
Story ID | Task | Assignee | Est. Pts | Actual Pts | Status | Start | End
US-21 | Fix BOM (Byte Order Mark) encoding issue in SecurityConfig.java that broke Docker builds | Ankush | 1 | 1 | Done | Mar 9 | Mar 11
US-21 | Code review and minor refactoring of auth service | Ankush | 2 | 2 | Done | Mar 11 | Mar 15
US-08 | Add JwtUtils for extracting user ID from bearer token in REST controllers | Aniket | 2 | 2 | Done | Mar 9 | Mar 13
US-22 | Build Profile page skeleton (tabs scaffolding, avatar) | Maurin | 2 | 2 | Done | Mar 9 | Mar 13
US-22 | Minor UI polish, navigation refinements, and bug fixes | Maurin | 2 | 2 | Done | Mar 13 | Mar 22
TOTAL | 5/5 tasks completed

## Sprint 4
Sprint 4 Backlog — Mar 23 – Apr 5, 2026 (light sprint)
Story ID | Task | Assignee | Est. Pts | Actual Pts | Status | Start | End
US-21 | Add /actuator/health endpoint configuration (preparation for load balancer health checks) | Ankush | 1 | 1 | Done | Mar 23 | Mar 25
US-21 | Add Javadoc and inline comments to auth service classes | Ankush | 2 | 2 | Done | Mar 25 | Apr 1
US-08 | Add input validation (Bean Validation) and UserNotFoundException across user/org endpoints | Aniket | 2 | 2 | Done | Mar 23 | Mar 30
US-08 | Test user and organization endpoints via Postman | Aniket | 1 | 1 | Done | Mar 30 | Apr 5
US-12 | Build Admin dashboard skeleton (tabs scaffolding, stat card placeholders) | Maurin | 2 | 2 | Done | Mar 23 | Mar 30
US-22 | Frontend bug fixes and minor responsive polish | Maurin | 2 | 2 | Done | Mar 30 | Apr 5
TOTAL | 6/6 tasks completed

## Sprint 5
Sprint 5 Backlog — Apr 6 – Apr 19, 2026 (catch-up sprint)
Story ID | Task | Assignee | Est. Pts | Actual Pts | Status | Start | End
US-08 | Bootstrap Event & Ticketing service (Spring Boot, Gradle): Event/Ticket entities, repositories, services | Ankush | 3 | 3 | Done | Apr 6 | Apr 8
US-08 | Implement EventController CRUD: GET /api/events (list/search), GET/POST/PUT/DELETE /api/events/{id} with Bean Validation (@Future, @Positive, @NotBlank) | Ankush | 4 | 4 | Done | Apr 8 | Apr 11
US-06 | Implement TicketController (purchase, my-tickets, refund) + admin moderation endpoints (dashboard, users, events, approve/reject) | Ankush | 4 | 4 | Done | Apr 11 | Apr 14
US-14 | Build EventPublisher (event.created, event.updated, event.cancelled) + PaymentListener consuming payment.completed/payment.failed | Ankush | 3 | 3 | Done | Apr 14 | Apr 16
US-21 | Implement Internal endpoints (InternalJwksController, InternalUserCreatedController) + final security review of all auth endpoints | Ankush | 3 | 3 | Done | Apr 16 | Apr 19
US-14 | Verify full RabbitMQ message flow end-to-end: auth → user → organization service | Aniket | 3 | 3 | Done | Apr 6 | Apr 10
US-20 | Implement notification consumer stub for ticket confirmation emails | Aniket | 3 | 3 | Done | Apr 10 | Apr 14
US-15 | Verify definitions.json correctly pre-loads all exchanges and queues; end-to-end testing of user/org service | Aniket | 3 | 3 | Done | Apr 14 | Apr 19
US-08 | Build organizer dashboard (event list, stats, create event button) + event creation form with all fields | Maurin | 4 | 4 | Done | Apr 6 | Apr 8
US-11 | Build admin dashboard with platform stats, pending approvals, and event moderation panel (4 tabs) | Maurin | 3 | 3 | Done | Apr 8 | Apr 10
US-06 | Implement mock payment flow with deterministic test cards (4242 success, 4000 0002 declined, etc.) + Payment Successful page | Maurin | 4 | 4 | Done | Apr 10 | Apr 12
US-22 | Build Profile page (4 tabs: Profile, Attending, Created, History) + Forgot/Reset/Verify Email pages | Maurin | 4 | 4 | Done | Apr 12 | Apr 14
US-09 | Build Organizations browser (2x2 grid) + Create Organization modal + attendee management page for organizers | Maurin | 3 | 3 | Done | Apr 14 | Apr 15
US-01 | Update register and deleteMe to call Supabase user_metadata + delete API with JWT token | Maurin | 2 | 2 | Done | Apr 15 | Apr 16
US-17 | Create IAM roles (EB service role + EC2 instance profile) + deploy auth JAR to AWS Elastic Beanstalk (sharks-auth-prod, Corretto 17) | Maurin | 4 | 4 | Done | Apr 16 | Apr 17
US-17 | Configure Application Load Balancer (public, multi-AZ, min 2 / max 4 t3.micro) + set EB environment variables | Maurin | 3 | 3 | Done | Apr 17 | Apr 18
US-18 | Set up Spring Cloud Gateway as routing layer + update api.ts to AWS endpoint + create demo accounts and test login through full AWS stack | Maurin | 3 | 3 | Done | Apr 18 | Apr 19
TOTAL | 17/17 tasks completed

## Sprint 6
Sprint 6 Backlog — Apr 20 – May 7, 2026
Story ID | Task | Assignee | Est. Pts | Actual Pts | Status | Start | End
US-21 | Final end-to-end testing of all auth endpoints through AWS stack (login, register, JWT validation) | Ankush | 2 | 2 | Done | Apr 20 | Apr 22
US-08 | Final end-to-end testing of Event & Ticketing service: event creation, ticket purchase, refund flow, admin approval | Ankush | 2 | 2 | Done | Apr 22 | Apr 25
US-14 | Verify EventPublisher and PaymentListener round-trip messaging across RabbitMQ in deployed environment | Ankush | 2 | 2 | Done | Apr 25 | Apr 28
US-17 | Verify load balancer routes correctly across both EC2 instances + Supabase RLS policies | Ankush | 2 | 2 | Done | Apr 28 | May 1
US-21 | Final GitHub push (auth + event service code, migrations, tests) with clean commit history | Ankush | 2 | 2 | Done | May 1 | May 7
US-15 | Final end-to-end testing of user/org APIs and full RabbitMQ pipeline | Aniket | 2 | 2 | Done | Apr 20 | Apr 24
US-14 | Document RabbitMQ messaging topology in MESSAGING.md with exchange/queue reference table | Aniket | 2 | 2 | Done | Apr 24 | Apr 27
US-15 | Final cleanup and documentation of user & organizations service + final GitHub push | Aniket | 2 | 2 | Done | Apr 27 | May 1
US-22 | Demo preparation and dry run of all 3 role logins (admin, organizer, attendee) | Aniket | 2 | 2 | Done | May 1 | May 7
US-19 | Connect custom domain sharks-eventbrite.live with Route 53 DNS configuration and SSL certificate | Maurin | 3 | 3 | Done | Apr 20 | Apr 22
US-17 | Update SecurityConfig CORS for sharks-eventbrite.live + www subdomain; rebuild and redeploy auth JAR (v1-2) | Maurin | 3 | 3 | Done | Apr 22 | Apr 24
US-22 | Create UI wireframes for all 15 screens across 3 user roles (Public, Attendee, Organizer, Admin) | Maurin | 4 | 4 | Done | Apr 24 | Apr 26
US-22 | Create UML Component diagram and Deployment diagram (final versions for AWS architecture) | Maurin | 3 | 3 | Done | Apr 26 | Apr 28
US-22 | Write README with full architecture, deployment instructions, demo accounts, troubleshooting | Maurin | 3 | 3 | Done | Apr 28 | Apr 30
US-22 | Create Scrum backlog spreadsheet with product backlog, sprint backlogs, and burndown chart | Maurin | 2 | 2 | Done | Apr 30 | May 1
US-22 | Write Project Journal with all 6 sprint scrum reports, XP values, and team contributions | Maurin | 3 | 3 | Done | May 1 | May 3
US-22 | Add Procfile and .ebextensions AWS deployment configs to repository | Maurin | 1 | 1 | Done | May 3 | May 4
US-20 | Final demo preparation, end-to-end dry run across all 3 role logins, polish remaining edge cases | Maurin | 2 | 2 | Done | May 4 | May 7
TOTAL | 18/18 tasks completed

## Burndown Chart
Project Burndown Chart — All 6 Sprints (Feb 9 – May 7, 2026)
Sprint Summary
Sprint | Dates | Total Points | Points Done | Points Remaining | Velocity (%)
1 | Feb 9 – Feb 22 | 40 | 40 | 0 | 100
2 | Feb 23 – Mar 8 | 45 | 45 | 0 | 100
3 | Mar 9 – Mar 22 | 9 | 9 | 0 | 100
4 | Mar 23 – Apr 5 | 10 | 10 | 0 | 100
5 | Apr 6 – Apr 19 | 56 | 56 | 0 | 100
6 | Apr 20 – May 7 | 42 | 42 | 0 | 100
TOTAL | Feb 9 – May 7
Sprint 6 Daily Burndown (Apr 20 – May 7, 2026)
Date | Ideal Remaining | Actual Remaining | Completed Today | Cumulative Done | Notes
Apr 20 | 42 | 42 | 0 | 0 | Sprint start
Apr 21 | 40 | 39 | 3 | 3 | Domain DNS setup
Apr 22 | 37 | 35 | 4 | 7 | Custom domain live + CORS update started
Apr 23 | 35 | 32 | 3 | 10 | JAR redeploy (v1-2)
Apr 24 | 32 | 29 | 3 | 13 | Wireframes started; user/org E2E testing
Apr 25 | 30 | 26 | 3 | 16 | Wireframes mid-progress
Apr 26 | 27 | 23 | 3 | 19 | Wireframes complete; UML diagrams started
Apr 27 | 25 | 20 | 3 | 22 | UML diagrams complete; MESSAGING.md docs
Apr 28 | 22 | 17 | 3 | 25 | README draft + event service E2E testing
Apr 29 | 20 | 14 | 3 | 28 | README complete
Apr 30 | 17 | 12 | 2 | 30 | Backlog spreadsheet
May 1 | 15 | 9 | 3 | 33 | Project Journal started; LB verification
May 2 | 12 | 7 | 2 | 35 | Project Journal in progress
May 3 | 10 | 5 | 2 | 37 | Journal complete + Procfile/.ebextensions
May 4 | 7 | 3 | 2 | 39 | Integration testing across services
May 5 | 5 | 1 | 2 | 41 | Demo dry run all 3 roles
May 6 | 2 | 0 | 1 | 42 | Final commits + cleanup
May 7 | 0 | 0 | 0 | 42 | Demo Day
Sprint Velocity Summary
Sprint | Points Planned | Points Completed
Sprint 1 | 40 | 40
Sprint 2 | 45 | 45
Sprint 3 | 9 | 9
Sprint 4 | 10 | 10
Sprint 5 | 56 | 56
Sprint 6 | 42 | 42